## Sheet1
Tasks | Effort | Member Responsible
1.0 Initiating
1.1 Research Information | 3 Days | Together
1.2 Decide Topic | 1 Day | Together
1.3 Learn to Use Arduino | 7 Days | Together
1.4 Oral Presentation | 1 Day | Together
1.5 Write Proposal | 1 Day | Together
1.6 Test Arduino with Sample Code | 2 Days | Together
2.0 Planning
2.1 Determine Require Parts and Componments | 3 Day | Together
2.2 Determine Project Budget | 1 Day | Together
2.3 Evaluate Bill of Materials | 1 Day | Yu Chen
2.4 Design Project Schedule | 1 Day | Huang Zheng
2.5 Make Gantt Chart | 1 DAY | Together
2.5 Assign Tasks | 1 DAY | Together
3.0 Excuting
3.1 Purchase Parts and Componments | 10 Days | Huang Zheng
3.2 Build Circuits on the Breadboard | 5 Days | Huang Zheng
3.3 Test Sensors with Code | 1 Day | Yu Chen
3.4 Build Each Individual Parts of Project & Promming Code | (4 Days) | (Together)
↘ 3.4.1 Cover with Light Sensor | 1 Day | Together
↘ 3.4.2 Soil Moisture Sensor + Water Pump + Motor Driver | 1 Day | Together
↘ 3.4.3 Fan with Motor Driver | 1 Day | Together
↘ 3.4.4 Heater | 1 Day | Together
3.5 Modify | 3 Days | Together
3.6 Combine All Parts Together | 7 Days | Together
3.7 Troubleshooting | 5 Days | Together
3.8 Make PCB & Soldering | 3 Days | Huang Zheng
3.9 Package The Project In a Case | 2 Days | Huang Zheng
4.0 Monitoring and Controlling
4.1 Control Scope | (3 Days) | (Together)
↘ 4.1.1 Make Sure Project Meet Requirment | 3 Days | Together
4.2 Contorl Cost | (1 Day) | (Together)
↘ 4.2.1 Rebudgeting | 1 Day | Together
5.0 Closing Project
5.1 Write Documentation | 3 Days | Together
5.2 Prepare The Presentation | 1 Days | Together
5.3 Final Check of Project | 1 Day | Together
5.4 Submit Project | 1 Day | Together
5.5 Submit Report | 1 Day | Together
5.6 Presentation | 1 Day | Together